## Sheet1
ID | Sprint 1 Task | Description | Assignee | Status
S1-01 | Analyze Source Systems | Analyze the available healthcare source systems and datasets | Smrithi, Febi, Harish | Done
S1-02 | Prepare Data Dictionary | Document fields, data types and descriptions for the datasets | Smrithi | Done
S1-03 | Develop 15 ETLs | Create 15 Pentaho transformations to ingest 15 datasets respectively | Febi | Done
S1-04 | Create Master Pentaho Job | Create a .kjb to execute all ingestion transformations | Febi | Done
S1-05 | Test ETL Pipeline | Execute the master Job and verify successful execution | Febi | Done
S1-06 | GitHub Update | Commit Pentaho transformations, Job and Sprint 1 documentation to GitHub | Smrithi, Febi, Harish | Done
S1-07 | Verify PostgreSQL Data | Check row counts, sample records, data types, null values, and successful loading. | Febi | Done
S1-08 | Commit ETL Artifacts to Git | Commit Pentaho .ktr, .kjb etc to Git. | Febi | Done
S1-09 | Prepare Sprint 1 PPT | Create the Sprint 1 presentation | Harish | Done